## Sheet1
# | Action Meeting 9 Oct 2018 | Who | Status
15 | Jurisdictional demonstrations to be included in future MDWG meeting agendas | MDWG Secretariat | Completed
16 | Shared Metadata Infrastructure | Andrew Whiting | In progress
# Define what this shared metadata infrastructure capability is in further detail
| # Establish a strong relationship with data.gov.au and explore their scope for hosting metadata, whilst ensuring custodians business requirements can be stained |  | Not done
17 | MDWG Secretariat to keep in touch with Nicholas Brown, monitoring GDA2020 developments and requirements of the group | MDWG Secretariat | Ongoing
18 | Prepare a web presence articulating the roadmap tranches | RMSG and Secretariat | In progress
19 | Circulate to the MDWG the deliverables roadmap spreadsheet for further feedback | MDWG Secretariat | Completed
20 | Explore a Trello board or other, to monitor the activities associated with the roadmap | MDWG Secretariat | Completed
21 | Have the roadmap status as a standing item on the groups agenda for status reporting | MDWG Secretariat | Completed
22 | Produce a narrative clearly articulating the proposed profile framework – explicitly articulating what it is and why it is different to past ANZLIC profile activities | Profile Sub Group | Completed
23 | Clearly articulate and describe what each of the elements is within the recommended profile comparison | Profile Sub Group | Completed
24 | Continue to make additions to the mapping spreadsheet – and document each of the jurisdiction mappings | Profile Sub Group , George Mansour | Ongoing
| # George Mansour to share with the PSG DELWP’s chosen elements, for inclusion in the mapping document |  | Completed
25 | Circulate the profile comparison to the MDWG for any further comment and feedback | MDWG Secretariat | Completed
26 | Develop and undertake a survey to identify what each MDWG’s metadata capabilities are identifying what systems or applications currently develop, manage or disseminate metadata | Profile Sub Group | Completed
27 | MDWG members interested in the technical working group to contact Irina.Bastrakova@ga.gov.au | All | Completed
28 | Kate Roberts (BOM), Ian Beitzel (Qld), Aaron Sedgmen (GA) and Adam Rice (DTA) wished to be included into this working group | Irina Bastrakova | Completed
29 | PSMA to be invited to the MDWG, with relation to the API associated activities | Irina Bastrakova | Completed
30 | Approach the Imagery Working Group, with a recommendation that the MDWG believe the 19115-2 standards need to be considered and worked upon. | Irina Bastrakova | Not done
31 | Defence, ACT, VIC, QLD and GA to define common requirements related to 19115-2, and 19165 standards. Consider how these requirements would be addressed within the associated standards |  | Not done
32 | Defence, ACT, VIC, QLD and GA to discuss further and report back to MDWG and the profile sub-group. |  | Not done
33 | Explore Trello and GovTeams for the hosting and management of the roadmap activities | MDWG Secretariat | Completed